## Menubar
Bug #BI_C_01
[Agro][Common Header] Menubar is shown perfectly in the top right corner
Status: | New | Start Date:
Priority: | Normal | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | Low | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-17 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Menubar Header | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser. 2. Check the menubar on the top right corner.
Actual Result:
Menubar is shown at the middle of the header.
Expected Result:
Menubar shown exactly at the top right corner

## Text alignment
Bug #BI_C_02
[Agro][Common] Perfect alignment of the text with the buttons
Status: | New | Start Date:
Priority: | Normal | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | Low | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-17 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Follow us bar | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser. 2. Check the follow up box
Actual Result:
Follow up text is showed at the right side and not aligned with the buttons
Expected Result:
Follow up text is aligned with the buttons at the left

## Popup Chatbox
Bug #BI_C_03
[Agro][Common] Showed a popup chat box perfectly
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-17 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Respond IO | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser. 2. Click on the website chat button
Actual Result:
Webchat doesn't show any popup box.
Expected Result:
Show a popup chat box perfectly

## Website Header
Bug #BI_HP_04
[Agro][Home page] Show the Website heading at the top of all content correctly
Status: | New | Start Date:
Priority: | Normal | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | Low | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-18 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Content Header | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser. 2. Check the content heading on the top of all content
Actual Result:
Heading is not properly aligned
Expected Result:
The heading will be accurate and text alignment shows perfectly.

## 7 Reason Content Header
Bug #BI_HP_05
[Agro][Home page] Contect heading and text document shows aligned and accurate
Status: | New | Start Date:
Priority: | Normal | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | Low | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-18 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | 7 reason headline and content | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser 2. Check the content and headline
Actual Result:
Heading background, heading, and content text are not showing properly and aligned
Expected Result:
The heading will be accurate and text alignment shows perfect

## Counting Status Bar
Bug #BI_HP_06
[Agro][Home page] Counting all the statistics accurately
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-18 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Counting Bar | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser 2. Check the counting statistics bar
Actual Result:
Visitors count doesn't show.
Expected Result:
Counting all the statistics accurately

## Post Show Card
Bug #BI_HP_07
[Agro][Home page] Redirect to the post show report successfully
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-18 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Card link section | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser 2. Click on the arrow sign
Actual Result:
Post show report card link is not there
Expected Result:
Redirect to the post show report successfully

## Exhibitor Manual
Bug #BI_HP_08
[Agro][Home page] Redirect to the exhibitors manual successfully
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-18 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Card link section | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available
Steps to Reproduce:
1. Visit the website through a browser 2. Click on the arrow sign
Actual Result:
Exhibitor manual card link is not there
Expected Result:
Redirect to the exhibitor manual successfully

## Cems Logo
Bug #BI_AU_09
[Agro][About us] Logo shows perfectly at the right bottom of the banner
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Banner | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the about us button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the cems logo at the bottom of the banner
Actual Result:
Logo is not there in tab and mobile devices.
Expected Result:
Logo shows perfectly at the right bottom of the banner.

## Cems content
Bug #BI_AU_10
[Agro][About us] Text content shows perfectly aligned and font and spellings are accurate
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Content | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the about us button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the text content
Actual Result:
One whole para of the content is missing
Expected Result:
Text content shows perfectly aligned and font and spellings are accurate

## Cems Image
Bug #BI_AU_11
[Agro][About us] Image shows perfectly at the left side of the content
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Cems image | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the about us button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the cems image
Actual Result:
Image is not there.
Expected Result:
Shows the image perfectly aligned with the content.

## Event profile Image
Bug #BI_EP_12
[Agro][Event Profile] Image shows perfectly at the right of the content
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Image | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the for exhibitor dropdown 5. User should click on the event profile button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the images
Actual Result:
Image is not there.
Expected Result:
Shows the images perfectly

## Why participate Image
Bug #BI_WP_13
[Agro][Why participate] Image shows perfectly at the right of the content
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Image | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the for exhibitor dropdown 5. User should click on the why participate button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the images
Actual Result:
Image is not there.
Expected Result:
Shows the images perfectly

## Why Bangladesh Image
Bug #BI_WB_14
[Agro][Why bangladesh] Image shows perfectly at the right of the content
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Image | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the for exhibitor dropdown 5. User should click on the why bangladesh button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the images
Actual Result:
Image is not there.
Expected Result:
Shows the images perfectly

## Exhibitor profile image
Bug #BI_POE_15
[Agro][Profile of exhibitor] Image shows perfectly at the right of the content
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Image | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the for exhibitor / for visitor dropdown 5. User should click on the profile of exhibitor / whom will you connect with button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the images
Actual Result:
Image is not there.
Expected Result:
Shows the images perfectly

## Why Visit Header
Bug #BI_WV_16
[Agro][Why Visit] Show the content heading at the top of all content correctly
Status: | New | Start Date:
Priority: | Normal | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | Low | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Content Header | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the for visitor dropdown 5. User should click on the why visit button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the content heading on the below m of the banner
Actual Result:
Heading background has changed
Expected Result:
The heading will be accurate and text alignment shows perfectly.

## Why Visit Image
Bug #BI_WV_17
[Agro][Why Visit] Shows the image perfectly in the right of 5 reason content
Status: | New | Start Date:
Priority: | High | Due Date:
Assignee: | Al Amin | % Done:
Category: | Website | Estimated Time:
Target Version: | Week 41-42 | Spent Time:
Severity: | High | Potential Impact of Fix:
Frequency: | 1 (Always) | Summary of Change:
Detected Version: | 1.0.0 | Actual Start Date:
Dected Date: | 2023-10-19 | Actual End Date:
Reproducibility: | Always | Requirement ID:
Detected OS Version: | Windows | Bug Background Analysis:
Area of Bug(Program Name): | Content Header | Task Owner:
Reproduce: |  | Defect Detected Phase:
Probable Cause of Bug: |  | Bug Type:
Identified Cause of Bug: |  | Bug Analysis:
Sprint: | 0.001
Description
Build: | 1.0.0
Agro_Bangladesh_1.0.0
Device:
Galaxy S9 Plus, iPhone XS, Mycell Comet & Sony Vaio S
Precondition:
1. Internet should be available 2. A web browser should be available 3. User should be on the websites home page 4. User should click on the for visitor dropdown 5. User should click on the why visit button
Steps to Reproduce:
1. Visit the website through a browser 2. Check the images at the right of the content
Actual Result:
Image is not there.
Expected Result:
Image shows perfectly at the right side of the content